## Detailed Status
68.42%
| 15.79% |  |  |  |  | Month 0 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8
Module | Demand / Description | Status | This Week | Next Week | Issues & Risks | Setember | October | November | December | January | February | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
Vehicle Sales | LOGISTIC - Integration between GDMC and factory system Support commercial area in Vehicle request and monitoring at IRA production factory Targets - Avoid manual task to request vehicle by IRA facotry. PIC: M. Pereira / Marcela / Sandro / Paulo |  | PHASE II GDMC (Status vehicle): IT Test : 90% complete. (On-hold resource replacement) - Knowledge transfer on-going. (Resource replacement) SAP (Conflict of Setup with Factory project): Development: On-hold due to SAP outage - The same resource works in the PI/PO setup | PHASE II GDMC: Knowledge transfer SAP - Setup conflict Evaluate the return of this task due to workload
| Tax Reform 2025 (Commercial system) Target - Compliance with legal requirement to ensure that GWM Brazil’s sales are not affected. |  | IT Test: On-going. So far, we have had two issues: one has been resolved and the other is currently being adjusted. | Keeping IT test until Dec, 12th
| Business segregation - Phase I 'Support GWM Brazil's plan to split the company into a sales subsidiary in order to benefit from the PIS and COFINS tax reduction. |  | Development: On-going as planned. | - Devlopment keep until Dec, 12th - Start the IT tests
Vehicle Sales | Leads - Add new leads fields in the interfaces Target - Reducing manual data manipulation and based on this increases the ensurance of LGPD compliance . - increase lead volume in 30%. - Reach the average market rate of lead conversion (7%) - Sales increase forecast R$ 49.000.000 (monthly) |  | User Test: Released to tests - Business request more time to perform the tests | Keep in UAT until Dec, 19th
| GDMC integration with Meta & Google Target - Increase lead conversion with better campaigns based on GDMC data inside of Meta and google. - Increase forecast sales R$ 4M. |  | ON HOLD – The business area will align with the agency, and once this alignment is completed, we will restart the initiative.
| LOGISTIC - RDC Car Managment - Integration between GDMC and HQ system Share BR vehicle with HQ system to restrict the vehicle moniting by Brazil Targets - Eliminate manual tasks to monitory batery level, fuel and other itens of cars in the RDC. PIC: Pereira / E. Standerski |  | User Test : Business area is no availability to perform the test
| Gboom code as SKU for local factory vehicle - Impact analysis Perform a end-to-end process in order to analyze impact to using G-Bom code as SKU for local fatocry vehicle Targets - Support tax legislation for the local factory vehicle - Enable solution to cover the current sales process without big changes. PIC: M. Pereira |  | IT teste: 50% complete | Finish IT test
After Sales | AFTER SALES - Spare Parts Price to DMS Targets - Increasing the eficiency avoiding manual errors - Reduce 575hrs (year) of business area to generate price information for each dealer - Reduced R$6,576.00 in tool costs per year.
|  |  | Go-Live done | Under monitoring
SAP Commercial | Symbolic transfer Perfom a symbolic transfer of the car to perfom the sales by Espirito Santo state. Targets - Recovery ICMS credit balance. PIC: Marcela / Sandro |  | Development: 90% (Pending user definition - mandatory change Request). High risk of workload with other projects
Data Lake | Vehicle service revision retention Identify vehicle revision time in order to booking service revision Target: - Avoiding manual task, 07:30hrs by months. - Increase 30% of revision services. PIC: M. Lopes |  | PHASE II: Channel Communcation Management UAT: License allocated to user User Test: IT is conducting tests together with the user - user on vacation until 05`Jan
| Top management KPIs. (President request) Generate top management KPIs to monitoring the commercial operation. (President request) Target: - One source data. - Official information of the company. PIC: M. Lopes |  | Phase I (Vehicle Sales) - The KPIs were presented to Mr. Andy, and we are now releasing them to the President and Country Manager for daily use. Mr. Zhang > Already Delivered Country Manager > To be delivered 'Start to work in details of new requirments of Mrs Andy Zhang | Estimate Next Deliverables for sales KPIs
| After Sales Tomorrow Guide PHASE I (NPS & WARRANTY) Generate a standard KPIs to evaluate dealer performance at after sales operations. Target: - Generate Operational KPIs. - Genarate Dealer Managment KPIs. - Generate Customer Satisfactions KPIs. PIC: M. Lopes |  | NPS - UAT: 80% complete Warranty - ON-HOLD - AMS contract finish | NPS - User on vacation
IT Commercial project status
UR
UR
Dev
UAT
IT Test
User Requirem
Development
IT Tests
User Test
User Req.
Development
IT Tests
GDMC - Phase I
GDMC - Phase II
UR
Dev
UAT
IT Test
Dev
UR
IT Test
Dev
Go-Live
User Req.
Dev
UAT
IT Test
SAP
Conception
Code review
IT Test
UAT
Go-Live
Knownledge Transfer
Impact analyze
Development
Dash Dev
IT Tests
UAT
Go-Live
Raising information to solve conflict
Dev
IT Test
KT
IT Test
IT Test
SAP outage
UAT
Go-Live
IT Test
On-hold - license expirantion
User Req
ETL Development
IT Tests
UAT
Go-Live
User Req
NPS
Warranty
ETL Development
On-hold
ETL Dev
On-hold
User Req
SAP outage
IT Test
Replanning
Wrokload- Project schedule conflict
Dev
Go-Live
IT Test
UAT
(First week to avoid sales closing period)
User Test
On-hold - License
UAT
Go-Live
IT Test
UR
Dev
UAT
User Req
User Availability
ST/UAT
Mandatory Change request
Dev
Go-Live
IT Test
UAT
Dev
Go-Live
IT Test
UAT
On-hold
Pending user Definition

## Sales Demand - Summary Report
| 15.79% | [9 empty] | May, 30th
| Status | Next Step | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Sales Demands | Quota : On time Go-Live: Done. National Stock Allocation : On-time IT Tests: 100% complete. User test: to be released to business area at Jun, 16th. 60 days age stock allocation : On-time IT Tests: 15% complete. | Quota - Under monitoring National Stock Allocation - User Test keep until Jun, 27th 60 days age stock allocation - IT Test keep until Jun, 20th
Payment retail order commission
Quota x Allocation Pilot
National Allocation
60 days age stock allocation
GDMC Purchase Order to Fatory
RDC Car Mgm - Int GDMC x HQ Sys
Stock Demands
(1,5 month Reduction)
Prioritized Demands
(2,5 Months reduction)
Tax reform & SAP segregation
2o Transportation comany - I
2o Transp Start
(4 months)
Summary Status - Priotized commercial IT demands
2o Transportation comany - II & III

## Summary Commercial Demands
|  |  | 15.79% | [14 empty] | May, 30th
|  | Project / Initiative | Status | Next Step | Apr | May | Jun |  |  | Jul |  |  |  | Aug | Sep | Oct | Nov | Dec
| Sales Demands | Quota x Allocation | GO-LIVE DONE
Sales Demands |  | National Stock Allocation | Under user test: to be finished at Jul, 18th due to sales closing period and salles planing team work replacement. | GO-LIVE: keep until Jun, 21th
60 days age stock allocation
2o transportation company
Fatory system & GDMC integrations
GDMC Whole Sales
Symbolic Transfer
Aundit System & GDMC Integration
Support to trade company replacement
|  | CRM | INCLUIR CRONOGRAMA
| Sales & After Sales | TAX REFORM
|  |  | Status | Next Step | Apr | May | Jun |  |  | Jul |  |  |  | Aug | Sep | Oct | Nov | Dec
SAP Commercial
[8 empty] | 24 | 30 | 8 | 15 | 21 | 28
|  |  | Status | Next Step | Apr | May | Jun |  |  | Jul |  |  |  | Aug | Sep | Oct | Nov | Dec
After Sales & Spare Parts
|  |  | Status | Next Step | Apr | May | Jun |  |  | Jul |  |  |  | Aug | Sep | Oct | Nov | Dec
Data Lake
|  |  | Status | Next Step | Apr | May | Jun |  |  | Jul |  |  |  | Aug | Sep | Oct | Nov | Dec
Whole Sales & Stock Transposition Demands (Commercial)
- Finalização pagamento de Fevereiro
- Iniciado o processo de pagamento de Março, Abril e Maio.
Quota x Allocation Pilot
National Allocation
60 days age stock allocation
GDMC Purchase Order to Fatory
Tax reform & SAP segregation
2o Transportation comany - I
Summary Commercial Demands - Priotized commercial IT demands
2o Transportation comany - II & III
GDMC Symbolic transfer
User Req
Dev
IT Test
UAT
GDMC x Factory (Status & PDI/Release Sales Vehicle)
User Req
Dev
IT Tests
UAT
Dev
UAT
IT Test
Service revision retention - Phase I - Contact Moment
UR
Dev
ST
UT
UR
Dev
ST ST
UT
"Reclame aqui" benchmarket KPI's
To be confirmed after User. Req.
After Sales Tomorrow Guide ( Dealer Evaluation)
To be confirmed after User. Req.
To be confirmed after User. Req.
Overview Logistic operation KPIs
Big Demand - Probably to be planned in phases
Big Demand - Probably to be planned in phases
Falta Assinatura da UR
Service revision retention -
Phase II - WhatsApp Customer Reminder
UR
Dev
ST
UT
To be confirmed after User. Req.
GDMC - Whole Sales Phase I
UR
Dev
ST
UT
GDMC - Whole Sales Phase II
UR
Dev
ST
UT
SAP - Whole Sales
UR
Dev
ST
UT
SAP - Stock Transposition
UR
Dev
ST
UT
GDMC VAAS Integration
User Req
Dev
IT Test
UAT
To be confirmed after User. Req.
To be confirmed after User. Req.
To be confirmed after User. Req.
1 - GDMC - Order to Fatory
- GDMC start to provide list of requested vehicles.
2 - GDMC - Status & PDI (Under analisys)
- GDMC integrate with fatcory system to provide the factory status.
- GDMC PDI must be integrate with Gabardo.
GDMC x VAAS
- Send Sales to COAF (Legal Requirement)
Symbolic Tranfer
- Recovery 78MI from ES State.
- Perform the sales by ES states, even, phisically, the car is other state.
Support new trade company
IT Test
UAT
Logistic - Replace Trade CIA
- New Cia will be addapt their system to use GWM developed APIs.
- Only Test support cover in this schedule
TAX Reform
- Mandatory legal requirement.
- in 2026 this is mandatory to sales cars and parts.
UR
Dev
ST
UT
UR
Dev
ST
UT
SAP - WRITER'S - Whole Sales
UR
Dev
ST
UT
SAP - WRITER'S - Stock Transposition
UR
Dev
ST
UT
SAP Resources
- Dev: Marilia /Antônio(AMS)
- GWM: Marcela
SAP Resources
- Dev: Cleber/Claudinei (AMS)
- GWM: Marcela
User Req.
Dev
UAT
ST
To be confirmed after User. Req.
SAP - FACTORY PROJECT - Conflict of Setup with
SAP Resources
- Dev: DANILO (AMS)
- GWM: Marcela
Dev
UR
ST
UAT
Go-Live
SAP - Symbolic Transfer
SAP - Conectivity Sales
UR
Dev
ST
UT
SAP Resources
- Dev: Marilia /Cleber (AMS)
- GWM: Marcela
Marcela Vacations
SAP Resources
- Dev: Marilia/Claudinei (AMS)
- GWM: Marcela
GDMC - Whole Sales Phase I
User Req.
Dev
IT Test
UAT
GDMC - Whole Sales Phase II
User Req.
Dev
IT Test
UAT
Whole Sales model
- Dedicated resources approval for that based on benefits of financial & commercial team
To be confirmed after User. Req.
To be confimed with business
To be confirmed after User. Req.
Parts Claim SAP Go-Live
GDMC - DSH
On-Hold
ST
UT
Support Chanels for Dealers ( Parts & Sales )
UR
Dev
ST
UT
Parts Claim Start Operation
UT
Effort To be confirmed
Effort confirmed
Legend
Effort To be confirmed
Effort confirmed
Legend
Effort To be confirmed
Effort confirmed
Legend
Parts Claim Start Operation
ST - SAP New Version
GDMC - Assesment changes- Tax Reform
GDMC customization - Tax Reform
GDMC - Test - Tax Reform
Plan A
- We need to keep with the Wholes Sales Resource due to knowledge of the system.
- Hiring new resources increase A LOT the risk of delay tax reform project.
<= Keep Whole Sales resources + 1 Full Stack -- 592Hrs -> 3,7 Rec (2,5/m) -> R$ 117K
<= 300Hrs -> 1,85 Rec (1,2/m) -> R$ 59K
<= 976Hrs -> 6 Rec (3/M) -> R$ 193.5K
<= 488,4Hrs -> 3 Rec (1,5/M) -> R$ 95.5K
Effort To be confirmed
Effort confirmed
Legend
Effort To be confirmed
Effort confirmed
Legend
Delivered
SAP - Whole Sales Phase I
User Req.
Dev
IT Test
UAT
Int Test
GDMC - DSH
On-Hold
ST
UT
Support Chanels for Dealers ( Parts & Sales )
UR
Dev
ST
UT
Parts Claim Start Operation
UT
Go-Live